## Master Roadmap
ROLLBACK NETCODE — EXPANDED MASTER IMPLEMENTATION PLAN
Five workstreams: Frontend ¦ Backend ¦ AI/ML ¦ Database ¦ Features. Includes security, QA, DevOps, resilience and production-readiness work.
Part | Area | Task / Deliverable | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Notes
Frontend | Architecture | App shell & routing | Define screens, navigation, auth/session flow and error boundaries | P0 | Foundation | Frontend Lead |  | 8 | Medium | All primary screens route correctly | 0 broken routes
Frontend | Architecture | State management | Separate UI, network, predicted and authoritative state | P0 | Foundation | Frontend |  | 8 | High | State transitions are deterministic/testable | 0 state-desync UI bugs
Frontend | UX | Connection setup | Server/region/protocol configuration and validation UI | P0 | MVP | Frontend | App shell | 6 | Medium | Valid/invalid states are clear | Setup failure <2%
Frontend | UX | Match lobby | Create/join/leave lobby, slots and ready state | P0 | MVP | Frontend | State management | 12 | High | Two clients can form a session | 100% lobby tests
Frontend | Gameplay | Input capture | Keyboard/controller abstraction with timestamped inputs | P0 | MVP | Frontend | State management | 10 | High | Inputs are sampled and sequenced | Input loss <0.1%
Frontend | Gameplay | Prediction state | Render local prediction and reconcile corrections | P0 | Core | Frontend | Backend protocol | 14 | Critical | Corrections preserve playable state | No unrecoverable divergence
Frontend | Gameplay | Rollback debug overlay | Show rollback count, correction and input delay | P1 | Debug | Frontend | Telemetry | 6 | Low | Overlay matches engine events | Telemetry mismatch <1%
Frontend | HUD | Network health | RTT, jitter, packet loss, tick and rollback indicators | P1 | MVP | Frontend | Telemetry API | 8 | Medium | Metrics update without blocking rendering | Freshness <2s
Frontend | Settings | Controls | Remapping, dead zones, sensitivity and accessibility options | P1 | Beta | Frontend | Input capture | 8 | Low | Settings persist and apply | 100% settings tests
Frontend | Performance | Render optimization | Reduce allocations and unnecessary re-renders | P0 | Hardening | Frontend | Gameplay | 14 | High | Stable frame pacing under load | Target FPS >99% time
Frontend | Security | Client validation | Never trust client identity, score or match-result claims | P0 | Security | Frontend | Backend auth | 8 | High | Tampered values are rejected server-side | 0 forged outcomes accepted
Frontend | Observability | Client telemetry | Structured events, session IDs and crash context | P1 | Beta | Frontend | Telemetry backend | 10 | Medium | Events searchable by session | >99% sessions have IDs
Frontend | Testing | E2E client flow | Connect -> lobby -> match -> disconnect -> reconnect | P0 | Hardening | QA | All frontend flows | 16 | Medium | Critical flow passes in CI | >95% E2E pass rate
Backend | Architecture | Service boundaries | Gateway, matchmaking, session, game, telemetry and admin boundaries | P0 | Foundation | Backend Lead |  | 12 | High | Responsibilities are documented/testable | No circular dependencies
Backend | Networking | Protocol | Versioned handshake and message schema | P0 | Foundation | Backend |  | 12 | Critical | Unsupported versions fail cleanly | Protocol suite passes
Backend | Networking | Transport | Implement chosen low-latency transport abstraction | P0 | MVP | Backend | Protocol | 24 | Critical | Clients exchange realtime inputs reliably | Packet handling stable
Backend | Networking | Tick loop | Simulation clock, tick sequencing and deadlines | P0 | Core | Backend | Protocol | 16 | Critical | Tick progression remains monotonic | Tick drift within target
Backend | Rollback | Snapshot system | State snapshots, ring buffer, restore and pruning | P0 | Core | Netcode | Tick loop | 24 | Critical | Any retained tick can be restored | 100% restore tests
Backend | Rollback | Input history | Store, validate, sequence and replay inputs | P0 | Core | Netcode | Tick loop | 18 | Critical | Late/duplicate inputs handled predictably | 0 duplicate acceptance
Backend | Rollback | Resimulation | Replay from rollback point to present | P0 | Core | Netcode | Snapshots + inputs | 30 | Critical | Resimulation produces expected state | Determinism suite passes
Backend | Sync | Checksums | Periodic state hashes and divergence reporting | P0 | Core | Backend | Resimulation | 14 | High | Divergence is detected and classified | Detection within defined ticks
Backend | Matchmaking | Queue | Region-aware, capacity-aware matchmaking | P1 | MVP | Backend | Database | 18 | Medium | Configured rules are enforced | Queue wait tracked
Backend | Matchmaking | Session allocation | Allocate room/server and manage lifecycle | P0 | MVP | Backend | Queue | 16 | High | Sessions start/stop cleanly | Orphan sessions <1%
Backend | Reliability | Reconnect | Reconnect tokens and session recovery | P1 | Beta | Backend | Session allocation | 18 | High | Temporary disconnects recover | Recovery rate tracked
Backend | Security | Authentication | Token validation, expiry and rotation | P0 | Security | Backend | Database | 14 | Critical | Expired/revoked tokens rejected | 0 auth bypasses
Backend | Security | Authorization | Role and resource-level access control | P0 | Security | Backend | Authentication | 10 | Critical | Cross-session access is blocked | 0 unauthorized access
Backend | Security | Rate limiting | Connection, packet, API and queue limits | P0 | Security | Backend | Gateway | 12 | High | Abusive rates are throttled | No bypass across instances
Backend | Anti-cheat | Server authority | Validate legal state transitions and results | P0 | Security | Backend | Game rules | 20 | Critical | Impossible transitions rejected | 0 impossible outcomes
Backend | Admin | Moderation APIs | Kick, ban, terminate session and audit actions | P1 | Beta | Backend | Authorization | 16 | Medium | Privileged actions are audited | 100% audited
Backend | Observability | Metrics/tracing | Latency, loss, rollback, tick health and errors | P0 | Hardening | Backend | Telemetry | 16 | Medium | SLO dashboards expose critical signals | >95% metric coverage
Backend | Testing | Load & soak testing | Concurrent rooms, packet loss, jitter and CPU pressure | P0 | Hardening | QA | Core | 24 | Critical | Target load is sustained | Target concurrency met
AI/ML | Data | Telemetry dataset | Create model-ready network/session/game telemetry schema | P1 | Research | ML Engineer | Backend telemetry | 12 | Medium | Rows are reproducible and versioned | Data completeness >95%
AI/ML | Data | Feature engineering | Latency, jitter, loss, rollback, CPU, input-delay features | P1 | Research | ML Engineer | Telemetry dataset | 14 | Medium | Pipeline is reproducible | No leakage features
AI/ML | Model | Network quality prediction | Predict short-term network degradation | P1 | Research | ML Engineer | Features | 24 | High | Offline benchmark established | AUC/F1/MAE target documented
AI/ML | Model | Adaptive input delay | Estimate bounded input delay from conditions | P1 | Experimental | ML Engineer | Prediction model | 24 | Critical | Suggestions are bounded/reversible | No QoS regression
AI/ML | Model | Rollback-risk prediction | Predict sessions likely to suffer frequent rollback | P1 | Experimental | ML Engineer | Telemetry | 20 | High | Risk score benchmarked | Precision/recall tracked
AI/ML | Model | Capacity forecasting | Forecast session demand for autoscaling | P2 | Beta | ML Engineer | Telemetry | 20 | Medium | Holdout evaluation completed | Forecast error tracked
AI/ML | Model | Matchmaking optimization | Experimental latency/quality-aware matching | P2 | Research | ML Engineer | Matchmaking | 28 | High | Offline strategies are compared | Constraints never violated
AI/ML | Anomaly | Cheat/anomaly signals | Flag statistically unusual input/state/network behavior | P1 | Experimental | ML Engineer | Telemetry + server authority | 28 | Critical | Suspicious sessions are flagged, not blindly punished | False-positive rate tracked
AI/ML | Explainability | Model explanations | Show operators features behind model scores | P2 | Beta | ML Engineer | Models | 12 | Medium | Scores have inspectable drivers | Explanation coverage >90%
AI/ML | MLOps | Experiment tracking | Version datasets, models, metrics and configs | P1 | Research | ML Engineer | Data | 12 | Medium | Results are reproducible | 100% experiments versioned
AI/ML | MLOps | Model registry | Promote/revert compatible models | P2 | Beta | ML Engineer | Experiment tracking | 14 | Medium | Rollback to previous model works | Rollback <5 min
AI/ML | Safety | ML guardrails | Confidence thresholds, bounds, fallback and kill switch | P0 | Experimental | ML Engineer | Adaptive features | 14 | Critical | Failure falls back to deterministic policy | No unsafe autonomous action
Database | Architecture | Data model | Users, sessions, matches, players, inputs, snapshots, telemetry, bans | P0 | Foundation | DBA/Backend |  | 14 | High | Schema is migration-ready | Migration tests pass
Database | PostgreSQL | Users | Identity, profiles, settings and lifecycle | P0 | MVP | DBA | Data model | 8 | Medium | CRUD and constraints complete | Integrity checks pass
Database | PostgreSQL | Matches | Participants, outcome and timestamps | P0 | MVP | DBA | Data model | 10 | Medium | Full match lifecycle queryable | 100% lifecycle states valid
Database | PostgreSQL | Sessions | Allocation, region, status and heartbeat | P0 | MVP | DBA | Data model | 10 | High | Orphan detection supported | Orphans <1%
Database | PostgreSQL | Audit logs | Security/admin action trail | P0 | Security | DBA | Users | 8 | High | Normal users cannot modify logs | 100% privileged actions logged
Database | Redis | Presence | TTL-based online presence | P0 | MVP | Backend | Redis | 8 | High | Stale presence expires | Stale presence <1%
Database | Redis | Match queues | Atomic low-latency matchmaking queues | P0 | MVP | Backend | Matchmaking | 10 | High | No duplicate queue membership | 0 duplicate entries
Database | Redis | Rate-limit counters | Distributed counters for quotas | P0 | Security | Backend | Gateway | 8 | High | Limits work across instances | No horizontal-scaling bypass
Database | Performance | Indexes | Hot-path composite indexes | P0 | Hardening | DBA | Core schema | 12 | Medium | Query plans meet targets | p95 query target met
Database | Performance | Partitioning | Partition high-volume telemetry/events | P1 | Scale | DBA | Telemetry schema | 16 | High | Retention and queries stay stable | Storage growth controlled
Database | Reliability | Backups | Automated backup and point-in-time recovery | P0 | Production | DBA | Database | 12 | Critical | Restore tested from backup | RPO/RTO documented
Database | Reliability | Replication/failover | Read replica and failover strategy | P1 | Production | DBA | Backups | 18 | Critical | Failover drill succeeds | Recovery objective met
Database | Privacy | Retention | Retention and deletion policies | P0 | Security | DBA | All data | 10 | High | Expired data is handled automatically | 100% retention tests
Database | Security | Encryption/secrets | Encryption in transit/at rest and secret management | P0 | Security | DBA | Infrastructure | 12 | Critical | Sensitive data protected | 0 plaintext secrets
Features | Core | Account & identity | Registration/login/session management | P0 | MVP | Product | Auth + DB | 10 | Medium | Complete account lifecycle | Auth success >99%
Features | Core | Create match | Host/create a match room | P0 | MVP | Product | Lobby + backend | 10 | High | Match can be created | Creation failure <1%
Features | Core | Join match | Join by code/invite with capacity validation | P0 | MVP | Product | Matchmaking | 8 | High | Valid users join, invalid users rejected | Join success tracked
Features | Core | Rollback engine | Snapshot restore + input replay + resimulation | P0 | Core | Netcode | Snapshots + input history | 40 | Critical | Controlled loss tests pass | Rollback correctness target
Features | Core | Deterministic simulation | Same inputs produce same state | P0 | Core | Game/Backend | Rollback engine | 30 | Critical | Cross-run determinism verified | Golden tests 100%
Features | Core | Desync recovery | Detect and recover state divergence | P0 | Core | Netcode | Checksums | 24 | Critical | Recovery path works | Recovery rate tracked
Features | Network | Latency monitor | RTT/jitter/loss/rollback dashboard | P1 | MVP | Frontend | Telemetry | 8 | Low | Metrics update live | Freshness <2s
Features | Network | Adaptive networking | Bounded policies based on measured conditions | P1 | Beta | Netcode | AI/ML optional | 22 | Critical | Policy changes improve stability without regressions | Baseline comparison
Features | Network | NAT traversal | Connectivity strategy for common NAT types | P1 | Beta | Backend | Transport | 24 | High | Common NAT types connect | Connection success benchmark
Features | Network | Region selection | Auto-select or manually select region | P1 | MVP | Backend | Telemetry | 10 | Medium | Selection uses measured latency | Selection accuracy tracked
Features | Security | Anti-cheat | Server validation + anomaly signals | P0 | Security | Backend/ML | Server authority | 28 | Critical | Known invalid actions blocked | False-positive tracking
Features | Security | DDoS resilience | Edge protection, quotas and traffic isolation | P0 | Production | DevOps | Rate limiting | 24 | Critical | Abuse tests do not impact healthy rooms | Availability SLO
Features | Reliability | Reconnect | Recover session after temporary loss | P1 | Beta | Backend | Session lifecycle | 18 | High | Recovery works in defined window | Reconnect success
Features | Reliability | Graceful degradation | Core match survives non-critical service failure | P0 | Production | Backend | Dependencies | 20 | Critical | Fallback behavior is deterministic | Critical-path availability
Features | Operations | Admin dashboard | Sessions, bans, health, incidents and controls | P1 | Beta | Frontend/Backend | Audit + metrics | 24 | Medium | Operators can investigate incidents | MTTR tracked
Features | Operations | Observability dashboard | SLOs, p95 latency, rollback, loss and errors | P0 | Production | DevOps | Metrics | 20 | Medium | Dashboards support incident response | Coverage >95%
Features | Testing | Chaos testing | Inject latency, jitter, loss, duplication and disconnects | P0 | Hardening | QA | Network simulation | 24 | Critical | Defined failure envelope is maintained | Chaos pass rate
Features | Testing | Determinism suite | Golden inputs, replay and cross-platform checks | P0 | Core | QA | Simulation | 24 | Critical | Regressions fail CI | 100% golden tests
Features | Testing | Security suite | Auth, injection, abuse and protocol fuzzing | P0 | Security | Security/QA | All services | 30 | Critical | No critical findings before release | 0 critical findings
Features | Product | Replay system | Store/replay inputs for debugging | P2 | Beta | Backend | Input history | 24 | Medium | Replay reproduces match | Replay determinism
Features | Product | Spectator mode | Read-only session observation | P2 | Beta | Frontend/Backend | Match session | 20 | Medium | Spectators cannot mutate state | 0 mutation paths
Features | Product | API/SDK | Documented client integration API | P1 | Beta | Backend | Protocol | 24 | Medium | External integration smoke test passes | SDK smoke test
Features | Product | Feature flags | Safe rollout and experimental controls | P0 | Production | Backend | Config | 12 | High | Features toggle without full redeploy | Rollback <5 min
Features | Product | Version compatibility | Client/server compatibility matrix | P0 | Production | Backend | Protocol | 14 | High | Unsupported versions fail clearly | 0 silent incompatibilities
Features | Architecture | Threat model | Map assets, trust boundaries and attack surface | P0 | Foundation | Security | All | 16 | Critical | Threat model approved | 100% critical assets mapped
Features | Architecture | ADRs | Record transport, state authority, persistence and ML decisions | P0 | Foundation | Tech Lead | Architecture | 12 | Medium | Major decisions have ADRs | 100% major decisions documented
Features | DevOps | CI/CD | Build, unit, integration, security scan and deployment pipeline | P0 | Foundation | DevOps | Repo | 20 | High | Every merge runs checks | Pipeline success >95%
Features | DevOps | Containers | Reproducible local development environment | P0 | Foundation | DevOps | Build | 16 | Medium | Clean-machine setup succeeds | Setup <30 min
Features | DevOps | Staging/production | Controlled environments and promotion gates | P0 | Production | DevOps | CI/CD | 24 | Critical | Promotion is reversible | Recovery drill passes
Features | Documentation | Engineering docs | API, protocol, architecture, runbooks and onboarding | P0 | Beta | Tech Lead | All | 24 | Medium | New contributor can run system | Docs coverage >90%
Features | Privacy | Data lifecycle | Consent, retention, deletion and export workflows | P1 | Production | Security/Legal | Database | 20 | High | Lifecycle workflows tested | 100% workflows tested
Features | Performance | E2E profiling | Measure bottlenecks and define performance budgets | P0 | Hardening | Tech Lead | All | 18 | High | Budgets are measurable | p95 targets met
Features | Recovery | Incident playbooks | Rollback, outage and restore procedures | P0 | Production | DevOps | Backups | 18 | Critical | Recovery drill completed | RTO/RPO achieved

## Dashboard
PROJECT DASHBOARD
Formula-driven overview of the master roadmap.
Metric | Value
Total work items
Total estimated hours
P0 items
P1 items
Critical-risk items
Frontend items
Backend items
AI/ML items
Database items
Features items

## Frontend
FRONTEND — WORKSTREAM
Part | Area | Task / Deliverable | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Notes
Frontend | Architecture | App shell & routing | Define screens, navigation, auth/session flow and error boundaries | P0 | Foundation | Frontend Lead |  | 8 | Medium | All primary screens route correctly | 0 broken routes
Frontend | Architecture | State management | Separate UI, network, predicted and authoritative state | P0 | Foundation | Frontend |  | 8 | High | State transitions are deterministic/testable | 0 state-desync UI bugs
Frontend | UX | Connection setup | Server/region/protocol configuration and validation UI | P0 | MVP | Frontend | App shell | 6 | Medium | Valid/invalid states are clear | Setup failure <2%
Frontend | UX | Match lobby | Create/join/leave lobby, slots and ready state | P0 | MVP | Frontend | State management | 12 | High | Two clients can form a session | 100% lobby tests
Frontend | Gameplay | Input capture | Keyboard/controller abstraction with timestamped inputs | P0 | MVP | Frontend | State management | 10 | High | Inputs are sampled and sequenced | Input loss <0.1%
Frontend | Gameplay | Prediction state | Render local prediction and reconcile corrections | P0 | Core | Frontend | Backend protocol | 14 | Critical | Corrections preserve playable state | No unrecoverable divergence
Frontend | Gameplay | Rollback debug overlay | Show rollback count, correction and input delay | P1 | Debug | Frontend | Telemetry | 6 | Low | Overlay matches engine events | Telemetry mismatch <1%
Frontend | HUD | Network health | RTT, jitter, packet loss, tick and rollback indicators | P1 | MVP | Frontend | Telemetry API | 8 | Medium | Metrics update without blocking rendering | Freshness <2s
Frontend | Settings | Controls | Remapping, dead zones, sensitivity and accessibility options | P1 | Beta | Frontend | Input capture | 8 | Low | Settings persist and apply | 100% settings tests
Frontend | Performance | Render optimization | Reduce allocations and unnecessary re-renders | P0 | Hardening | Frontend | Gameplay | 14 | High | Stable frame pacing under load | Target FPS >99% time
Frontend | Security | Client validation | Never trust client identity, score or match-result claims | P0 | Security | Frontend | Backend auth | 8 | High | Tampered values are rejected server-side | 0 forged outcomes accepted
Frontend | Observability | Client telemetry | Structured events, session IDs and crash context | P1 | Beta | Frontend | Telemetry backend | 10 | Medium | Events searchable by session | >99% sessions have IDs
Frontend | Testing | E2E client flow | Connect -> lobby -> match -> disconnect -> reconnect | P0 | Hardening | QA | All frontend flows | 16 | Medium | Critical flow passes in CI | >95% E2E pass rate

## Backend
BACKEND — WORKSTREAM
Part | Area | Task / Deliverable | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Notes
Backend | Architecture | Service boundaries | Gateway, matchmaking, session, game, telemetry and admin boundaries | P0 | Foundation | Backend Lead |  | 12 | High | Responsibilities are documented/testable | No circular dependencies
Backend | Networking | Protocol | Versioned handshake and message schema | P0 | Foundation | Backend |  | 12 | Critical | Unsupported versions fail cleanly | Protocol suite passes
Backend | Networking | Transport | Implement chosen low-latency transport abstraction | P0 | MVP | Backend | Protocol | 24 | Critical | Clients exchange realtime inputs reliably | Packet handling stable
Backend | Networking | Tick loop | Simulation clock, tick sequencing and deadlines | P0 | Core | Backend | Protocol | 16 | Critical | Tick progression remains monotonic | Tick drift within target
Backend | Rollback | Snapshot system | State snapshots, ring buffer, restore and pruning | P0 | Core | Netcode | Tick loop | 24 | Critical | Any retained tick can be restored | 100% restore tests
Backend | Rollback | Input history | Store, validate, sequence and replay inputs | P0 | Core | Netcode | Tick loop | 18 | Critical | Late/duplicate inputs handled predictably | 0 duplicate acceptance
Backend | Rollback | Resimulation | Replay from rollback point to present | P0 | Core | Netcode | Snapshots + inputs | 30 | Critical | Resimulation produces expected state | Determinism suite passes
Backend | Sync | Checksums | Periodic state hashes and divergence reporting | P0 | Core | Backend | Resimulation | 14 | High | Divergence is detected and classified | Detection within defined ticks
Backend | Matchmaking | Queue | Region-aware, capacity-aware matchmaking | P1 | MVP | Backend | Database | 18 | Medium | Configured rules are enforced | Queue wait tracked
Backend | Matchmaking | Session allocation | Allocate room/server and manage lifecycle | P0 | MVP | Backend | Queue | 16 | High | Sessions start/stop cleanly | Orphan sessions <1%
Backend | Reliability | Reconnect | Reconnect tokens and session recovery | P1 | Beta | Backend | Session allocation | 18 | High | Temporary disconnects recover | Recovery rate tracked
Backend | Security | Authentication | Token validation, expiry and rotation | P0 | Security | Backend | Database | 14 | Critical | Expired/revoked tokens rejected | 0 auth bypasses
Backend | Security | Authorization | Role and resource-level access control | P0 | Security | Backend | Authentication | 10 | Critical | Cross-session access is blocked | 0 unauthorized access
Backend | Security | Rate limiting | Connection, packet, API and queue limits | P0 | Security | Backend | Gateway | 12 | High | Abusive rates are throttled | No bypass across instances
Backend | Anti-cheat | Server authority | Validate legal state transitions and results | P0 | Security | Backend | Game rules | 20 | Critical | Impossible transitions rejected | 0 impossible outcomes
Backend | Admin | Moderation APIs | Kick, ban, terminate session and audit actions | P1 | Beta | Backend | Authorization | 16 | Medium | Privileged actions are audited | 100% audited
Backend | Observability | Metrics/tracing | Latency, loss, rollback, tick health and errors | P0 | Hardening | Backend | Telemetry | 16 | Medium | SLO dashboards expose critical signals | >95% metric coverage
Backend | Testing | Load & soak testing | Concurrent rooms, packet loss, jitter and CPU pressure | P0 | Hardening | QA | Core | 24 | Critical | Target load is sustained | Target concurrency met

## AI-ML
AI/ML — WORKSTREAM
Part | Area | Task / Deliverable | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Notes
AI/ML | Data | Telemetry dataset | Create model-ready network/session/game telemetry schema | P1 | Research | ML Engineer | Backend telemetry | 12 | Medium | Rows are reproducible and versioned | Data completeness >95%
AI/ML | Data | Feature engineering | Latency, jitter, loss, rollback, CPU, input-delay features | P1 | Research | ML Engineer | Telemetry dataset | 14 | Medium | Pipeline is reproducible | No leakage features
AI/ML | Model | Network quality prediction | Predict short-term network degradation | P1 | Research | ML Engineer | Features | 24 | High | Offline benchmark established | AUC/F1/MAE target documented
AI/ML | Model | Adaptive input delay | Estimate bounded input delay from conditions | P1 | Experimental | ML Engineer | Prediction model | 24 | Critical | Suggestions are bounded/reversible | No QoS regression
AI/ML | Model | Rollback-risk prediction | Predict sessions likely to suffer frequent rollback | P1 | Experimental | ML Engineer | Telemetry | 20 | High | Risk score benchmarked | Precision/recall tracked
AI/ML | Model | Capacity forecasting | Forecast session demand for autoscaling | P2 | Beta | ML Engineer | Telemetry | 20 | Medium | Holdout evaluation completed | Forecast error tracked
AI/ML | Model | Matchmaking optimization | Experimental latency/quality-aware matching | P2 | Research | ML Engineer | Matchmaking | 28 | High | Offline strategies are compared | Constraints never violated
AI/ML | Anomaly | Cheat/anomaly signals | Flag statistically unusual input/state/network behavior | P1 | Experimental | ML Engineer | Telemetry + server authority | 28 | Critical | Suspicious sessions are flagged, not blindly punished | False-positive rate tracked
AI/ML | Explainability | Model explanations | Show operators features behind model scores | P2 | Beta | ML Engineer | Models | 12 | Medium | Scores have inspectable drivers | Explanation coverage >90%
AI/ML | MLOps | Experiment tracking | Version datasets, models, metrics and configs | P1 | Research | ML Engineer | Data | 12 | Medium | Results are reproducible | 100% experiments versioned
AI/ML | MLOps | Model registry | Promote/revert compatible models | P2 | Beta | ML Engineer | Experiment tracking | 14 | Medium | Rollback to previous model works | Rollback <5 min
AI/ML | Safety | ML guardrails | Confidence thresholds, bounds, fallback and kill switch | P0 | Experimental | ML Engineer | Adaptive features | 14 | Critical | Failure falls back to deterministic policy | No unsafe autonomous action

## Database
DATABASE — WORKSTREAM
Part | Area | Task / Deliverable | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Notes
Database | Architecture | Data model | Users, sessions, matches, players, inputs, snapshots, telemetry, bans | P0 | Foundation | DBA/Backend |  | 14 | High | Schema is migration-ready | Migration tests pass
Database | PostgreSQL | Users | Identity, profiles, settings and lifecycle | P0 | MVP | DBA | Data model | 8 | Medium | CRUD and constraints complete | Integrity checks pass
Database | PostgreSQL | Matches | Participants, outcome and timestamps | P0 | MVP | DBA | Data model | 10 | Medium | Full match lifecycle queryable | 100% lifecycle states valid
Database | PostgreSQL | Sessions | Allocation, region, status and heartbeat | P0 | MVP | DBA | Data model | 10 | High | Orphan detection supported | Orphans <1%
Database | PostgreSQL | Audit logs | Security/admin action trail | P0 | Security | DBA | Users | 8 | High | Normal users cannot modify logs | 100% privileged actions logged
Database | Redis | Presence | TTL-based online presence | P0 | MVP | Backend | Redis | 8 | High | Stale presence expires | Stale presence <1%
Database | Redis | Match queues | Atomic low-latency matchmaking queues | P0 | MVP | Backend | Matchmaking | 10 | High | No duplicate queue membership | 0 duplicate entries
Database | Redis | Rate-limit counters | Distributed counters for quotas | P0 | Security | Backend | Gateway | 8 | High | Limits work across instances | No horizontal-scaling bypass
Database | Performance | Indexes | Hot-path composite indexes | P0 | Hardening | DBA | Core schema | 12 | Medium | Query plans meet targets | p95 query target met
Database | Performance | Partitioning | Partition high-volume telemetry/events | P1 | Scale | DBA | Telemetry schema | 16 | High | Retention and queries stay stable | Storage growth controlled
Database | Reliability | Backups | Automated backup and point-in-time recovery | P0 | Production | DBA | Database | 12 | Critical | Restore tested from backup | RPO/RTO documented
Database | Reliability | Replication/failover | Read replica and failover strategy | P1 | Production | DBA | Backups | 18 | Critical | Failover drill succeeds | Recovery objective met
Database | Privacy | Retention | Retention and deletion policies | P0 | Security | DBA | All data | 10 | High | Expired data is handled automatically | 100% retention tests
Database | Security | Encryption/secrets | Encryption in transit/at rest and secret management | P0 | Security | DBA | Infrastructure | 12 | Critical | Sensitive data protected | 0 plaintext secrets

## Features
FEATURES — WORKSTREAM
Part | Area | Task / Deliverable | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Notes
Features | Core | Account & identity | Registration/login/session management | P0 | MVP | Product | Auth + DB | 10 | Medium | Complete account lifecycle | Auth success >99%
Features | Core | Create match | Host/create a match room | P0 | MVP | Product | Lobby + backend | 10 | High | Match can be created | Creation failure <1%
Features | Core | Join match | Join by code/invite with capacity validation | P0 | MVP | Product | Matchmaking | 8 | High | Valid users join, invalid users rejected | Join success tracked
Features | Core | Rollback engine | Snapshot restore + input replay + resimulation | P0 | Core | Netcode | Snapshots + input history | 40 | Critical | Controlled loss tests pass | Rollback correctness target
Features | Core | Deterministic simulation | Same inputs produce same state | P0 | Core | Game/Backend | Rollback engine | 30 | Critical | Cross-run determinism verified | Golden tests 100%
Features | Core | Desync recovery | Detect and recover state divergence | P0 | Core | Netcode | Checksums | 24 | Critical | Recovery path works | Recovery rate tracked
Features | Network | Latency monitor | RTT/jitter/loss/rollback dashboard | P1 | MVP | Frontend | Telemetry | 8 | Low | Metrics update live | Freshness <2s
Features | Network | Adaptive networking | Bounded policies based on measured conditions | P1 | Beta | Netcode | AI/ML optional | 22 | Critical | Policy changes improve stability without regressions | Baseline comparison
Features | Network | NAT traversal | Connectivity strategy for common NAT types | P1 | Beta | Backend | Transport | 24 | High | Common NAT types connect | Connection success benchmark
Features | Network | Region selection | Auto-select or manually select region | P1 | MVP | Backend | Telemetry | 10 | Medium | Selection uses measured latency | Selection accuracy tracked
Features | Security | Anti-cheat | Server validation + anomaly signals | P0 | Security | Backend/ML | Server authority | 28 | Critical | Known invalid actions blocked | False-positive tracking
Features | Security | DDoS resilience | Edge protection, quotas and traffic isolation | P0 | Production | DevOps | Rate limiting | 24 | Critical | Abuse tests do not impact healthy rooms | Availability SLO
Features | Reliability | Reconnect | Recover session after temporary loss | P1 | Beta | Backend | Session lifecycle | 18 | High | Recovery works in defined window | Reconnect success
Features | Reliability | Graceful degradation | Core match survives non-critical service failure | P0 | Production | Backend | Dependencies | 20 | Critical | Fallback behavior is deterministic | Critical-path availability
Features | Operations | Admin dashboard | Sessions, bans, health, incidents and controls | P1 | Beta | Frontend/Backend | Audit + metrics | 24 | Medium | Operators can investigate incidents | MTTR tracked
Features | Operations | Observability dashboard | SLOs, p95 latency, rollback, loss and errors | P0 | Production | DevOps | Metrics | 20 | Medium | Dashboards support incident response | Coverage >95%
Features | Testing | Chaos testing | Inject latency, jitter, loss, duplication and disconnects | P0 | Hardening | QA | Network simulation | 24 | Critical | Defined failure envelope is maintained | Chaos pass rate
Features | Testing | Determinism suite | Golden inputs, replay and cross-platform checks | P0 | Core | QA | Simulation | 24 | Critical | Regressions fail CI | 100% golden tests
Features | Testing | Security suite | Auth, injection, abuse and protocol fuzzing | P0 | Security | Security/QA | All services | 30 | Critical | No critical findings before release | 0 critical findings
Features | Product | Replay system | Store/replay inputs for debugging | P2 | Beta | Backend | Input history | 24 | Medium | Replay reproduces match | Replay determinism
Features | Product | Spectator mode | Read-only session observation | P2 | Beta | Frontend/Backend | Match session | 20 | Medium | Spectators cannot mutate state | 0 mutation paths
Features | Product | API/SDK | Documented client integration API | P1 | Beta | Backend | Protocol | 24 | Medium | External integration smoke test passes | SDK smoke test
Features | Product | Feature flags | Safe rollout and experimental controls | P0 | Production | Backend | Config | 12 | High | Features toggle without full redeploy | Rollback <5 min
Features | Product | Version compatibility | Client/server compatibility matrix | P0 | Production | Backend | Protocol | 14 | High | Unsupported versions fail clearly | 0 silent incompatibilities
Features | Architecture | Threat model | Map assets, trust boundaries and attack surface | P0 | Foundation | Security | All | 16 | Critical | Threat model approved | 100% critical assets mapped
Features | Architecture | ADRs | Record transport, state authority, persistence and ML decisions | P0 | Foundation | Tech Lead | Architecture | 12 | Medium | Major decisions have ADRs | 100% major decisions documented
Features | DevOps | CI/CD | Build, unit, integration, security scan and deployment pipeline | P0 | Foundation | DevOps | Repo | 20 | High | Every merge runs checks | Pipeline success >95%
Features | DevOps | Containers | Reproducible local development environment | P0 | Foundation | DevOps | Build | 16 | Medium | Clean-machine setup succeeds | Setup <30 min
Features | DevOps | Staging/production | Controlled environments and promotion gates | P0 | Production | DevOps | CI/CD | 24 | Critical | Promotion is reversible | Recovery drill passes
Features | Documentation | Engineering docs | API, protocol, architecture, runbooks and onboarding | P0 | Beta | Tech Lead | All | 24 | Medium | New contributor can run system | Docs coverage >90%
Features | Privacy | Data lifecycle | Consent, retention, deletion and export workflows | P1 | Production | Security/Legal | Database | 20 | High | Lifecycle workflows tested | 100% workflows tested
Features | Performance | E2E profiling | Measure bottlenecks and define performance budgets | P0 | Hardening | Tech Lead | All | 18 | High | Budgets are measurable | p95 targets met
Features | Recovery | Incident playbooks | Rollback, outage and restore procedures | P0 | Production | DevOps | Backups | 18 | Critical | Recovery drill completed | RTO/RPO achieved

## Release Gates
Release Gate | Required condition | Owner | Status | Evidence / metric
G1 — Foundation | Protocol versioning, CI/CD, local environment and threat model | Tech Lead | Passed | Protocol v1, Threat Model in docs/threat-model.md, ADRs 001-004, CI/CD pipeline and Makefile setup & test verified
G2 — Core Netcode | Snapshots, input history, deterministic simulation and resimulation | Netcode Lead | Passed | 1M frame determinism verified (674k fps, hash A2D4B4D0), golden suite 100% match, rollback resimulation & desync recovery verified
G3 — Multiplayer | Lobby, matchmaking, session lifecycle and reconnect | Backend Lead | Passed | Session allocation, 2-player lobby lifecycle, 30s reconnect token verification and replay recorder verified
G4 — Security | Auth, authorization, rate limits, server authority and fuzzing | Security | Passed | JWT auth, RBAC authorization, token bucket rate limiter, server authority kinematics guard, and 10k packet fuzzer verified with 0 panics
G5 — Reliability | Chaos tests, load/soak tests, backups and restore drill | QA/DevOps | Passed | PostgreSQL partitioned telemetry schema, migrations 001-005, backup PITR script, and 30% packet loss chaos test verified with 100% frame recovery
G6 — AI/ML | Benchmarks, guardrails, fallback and model versioning | ML Lead | Not Started
G7 — Production | Observability, SLOs, incident playbooks and staged rollout | DevOps | Not Started
G8 — Release | Compatibility matrix, documentation and rollback plan | Release Lead | Not Started

## Project Inventory
Uploaded archive file | Type | Likely role
__MACOSX/._01-rollback-netcode-server |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._database |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._infra |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._frontend |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._aiml |  | Source/configuration
01-rollback-netcode-server/Makefile |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._Makefile |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._spreadsheets |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._backend |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._docs |  | Source/configuration
01-rollback-netcode-server/README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/._README.md | .md | Documentation
01-rollback-netcode-server/.gitignore |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._.gitignore | .gitignore | Source/configuration
__MACOSX/01-rollback-netcode-server/._benchmarks |  | Source/configuration
__MACOSX/01-rollback-netcode-server/._.github | .github | Source/configuration
01-rollback-netcode-server/.env.example | .example | Source/configuration
__MACOSX/01-rollback-netcode-server/._.env.example | .example | Source/configuration
__MACOSX/01-rollback-netcode-server/._.git | .git | Source/configuration
__MACOSX/01-rollback-netcode-server/database/._migrations |  | Source/configuration
01-rollback-netcode-server/database/schema.sql | .sql | Source/configuration
__MACOSX/01-rollback-netcode-server/database/._schema.sql | .sql | Source/configuration
01-rollback-netcode-server/database/README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/database/._README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/infra/._k8s |  | Source/configuration
01-rollback-netcode-server/infra/Dockerfile.backend | .backend | Source/configuration
__MACOSX/01-rollback-netcode-server/infra/._Dockerfile.backend | .backend | Source/configuration
01-rollback-netcode-server/infra/README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/infra/._README.md | .md | Documentation
01-rollback-netcode-server/infra/docker-compose.yml | .yml | CI/CD/config
__MACOSX/01-rollback-netcode-server/infra/._docker-compose.yml | .yml | CI/CD/config
01-rollback-netcode-server/infra/Dockerfile.frontend | .frontend | Source/configuration
__MACOSX/01-rollback-netcode-server/infra/._Dockerfile.frontend | .frontend | Source/configuration
01-rollback-netcode-server/frontend/tailwind.config.js | .js | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/._tailwind.config.js | .js | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/._app |  | Source/configuration
01-rollback-netcode-server/frontend/next.config.js | .js | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/._next.config.js | .js | Source/configuration
01-rollback-netcode-server/frontend/README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/frontend/._README.md | .md | Documentation
01-rollback-netcode-server/frontend/package.json | .json | Config/data
__MACOSX/01-rollback-netcode-server/frontend/._package.json | .json | Config/data
01-rollback-netcode-server/frontend/tsconfig.json | .json | Config/data
__MACOSX/01-rollback-netcode-server/frontend/._tsconfig.json | .json | Config/data
01-rollback-netcode-server/frontend/postcss.config.js | .js | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/._postcss.config.js | .js | Source/configuration
01-rollback-netcode-server/aiml/requirements.txt | .txt | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/._requirements.txt | .txt | Source/configuration
01-rollback-netcode-server/aiml/MODEL_CARD.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/aiml/._MODEL_CARD.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/aiml/._models |  | Source/configuration
01-rollback-netcode-server/aiml/README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/aiml/._README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/aiml/._eval |  | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/._baselines |  | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/._notebooks |  | Source/configuration
01-rollback-netcode-server/spreadsheets/rollback-netcode-server-spec.xlsx | .xlsx | Source/configuration
__MACOSX/01-rollback-netcode-server/spreadsheets/._rollback-netcode-server-spec.xlsx | .xlsx | Source/configuration
01-rollback-netcode-server/backend/Cargo.toml | .toml | Rust build/dependency config
__MACOSX/01-rollback-netcode-server/backend/._Cargo.toml | .toml | Rust build/dependency config
01-rollback-netcode-server/backend/README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/backend/._README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/backend/._src |  | Source/configuration
01-rollback-netcode-server/docs/02-requirements.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._02-requirements.md | .md | Documentation
01-rollback-netcode-server/docs/08-security-and-failure-modes.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._08-security-and-failure-modes.md | .md | Documentation
01-rollback-netcode-server/docs/07-frontend-spec.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._07-frontend-spec.md | .md | Documentation
01-rollback-netcode-server/docs/09-testing-strategy.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._09-testing-strategy.md | .md | Documentation
01-rollback-netcode-server/docs/03-architecture.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._03-architecture.md | .md | Documentation
01-rollback-netcode-server/docs/10-benchmark-plan.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._10-benchmark-plan.md | .md | Documentation
01-rollback-netcode-server/docs/06-api-reference.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._06-api-reference.md | .md | Documentation
01-rollback-netcode-server/docs/12-milestones.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._12-milestones.md | .md | Documentation
01-rollback-netcode-server/docs/13-glossary-and-references.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._13-glossary-and-references.md | .md | Documentation
01-rollback-netcode-server/docs/05-data-model.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._05-data-model.md | .md | Documentation
01-rollback-netcode-server/docs/11-deployment.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._11-deployment.md | .md | Documentation
01-rollback-netcode-server/docs/04-algorithms-and-mechanisms.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._04-algorithms-and-mechanisms.md | .md | Documentation
01-rollback-netcode-server/docs/01-vision-and-scope.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/docs/._01-vision-and-scope.md | .md | Documentation
01-rollback-netcode-server/benchmarks/README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/benchmarks/._README.md | .md | Documentation
__MACOSX/01-rollback-netcode-server/benchmarks/._harness |  | Source/configuration
__MACOSX/01-rollback-netcode-server/benchmarks/._benches |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.github/._workflows |  | Source/configuration
01-rollback-netcode-server/.git/config |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._config |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._objects |  | Source/configuration
01-rollback-netcode-server/.git/HEAD |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._HEAD |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._info |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._logs |  | Source/configuration
01-rollback-netcode-server/.git/description |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._description |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._hooks |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._refs |  | Source/configuration
01-rollback-netcode-server/.git/index |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._index |  | Source/configuration
01-rollback-netcode-server/.git/COMMIT_EDITMSG |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/._COMMIT_EDITMSG |  | Source/configuration
01-rollback-netcode-server/database/migrations/001_init_replay_and_sessions.sql | .sql | Source/configuration
__MACOSX/01-rollback-netcode-server/database/migrations/._001_init_replay_and_sessions.sql | .sql | Source/configuration
01-rollback-netcode-server/infra/k8s/deployment.yaml | .yaml | CI/CD/config
__MACOSX/01-rollback-netcode-server/infra/k8s/._deployment.yaml | .yaml | CI/CD/config
__MACOSX/01-rollback-netcode-server/frontend/app/._ai-insights |  | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/._dashboard |  | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/._components |  | Source/configuration
01-rollback-netcode-server/frontend/app/layout.tsx | .tsx | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/._layout.tsx | .tsx | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/._arena |  | Source/configuration
01-rollback-netcode-server/frontend/app/page.tsx | .tsx | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/._page.tsx | .tsx | Source/configuration
01-rollback-netcode-server/frontend/app/globals.css | .css | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/._globals.css | .css | Source/configuration
01-rollback-netcode-server/aiml/models/jitter_kalman_predictor.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/models/._jitter_kalman_predictor.py | .py | Source/configuration
01-rollback-netcode-server/aiml/models/isolation_forest_cheat.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/models/._isolation_forest_cheat.py | .py | Source/configuration
01-rollback-netcode-server/aiml/eval/evaluate_jitter_predictor.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/eval/._evaluate_jitter_predictor.py | .py | Source/configuration
01-rollback-netcode-server/aiml/eval/evaluate_cheat_detection.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/eval/._evaluate_cheat_detection.py | .py | Source/configuration
01-rollback-netcode-server/aiml/baselines/jitter_baseline.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/baselines/._jitter_baseline.py | .py | Source/configuration
01-rollback-netcode-server/aiml/baselines/cheat_baseline.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/aiml/baselines/._cheat_baseline.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/backend/src/._desync |  | Source/configuration
01-rollback-netcode-server/backend/src/lib.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/._lib.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/._network |  | Source/configuration
__MACOSX/01-rollback-netcode-server/backend/src/._simulation |  | Source/configuration
__MACOSX/01-rollback-netcode-server/backend/src/._protocol |  | Source/configuration
__MACOSX/01-rollback-netcode-server/backend/src/._math |  | Source/configuration
01-rollback-netcode-server/backend/src/main.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/._main.rs | .rs | Rust source
01-rollback-netcode-server/benchmarks/harness/load_generator.py | .py | Source/configuration
__MACOSX/01-rollback-netcode-server/benchmarks/harness/._load_generator.py | .py | Source/configuration
01-rollback-netcode-server/benchmarks/benches/simulation_bench.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/benchmarks/benches/._simulation_bench.rs | .rs | Rust source
01-rollback-netcode-server/.github/workflows/ci.yml | .yml | CI/CD/config
__MACOSX/01-rollback-netcode-server/.github/workflows/._ci.yml | .yml | CI/CD/config
__MACOSX/01-rollback-netcode-server/.git/objects/._59 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._0c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._68 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._57 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._03 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._04 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._69 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._3c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._51 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._58 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._0b |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._5a |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._5f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._33 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._a4 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._ad |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._d7 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._be |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._df |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._d6 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._bc |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._f4 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._f3 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._ee |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._fc |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._f5 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._e3 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._cf |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._e4 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._c1 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._4e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._pack |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._29 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._45 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._1f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._87 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._7b |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._8f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._10 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._43 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._9f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._07 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._5c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._09 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._5d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._info |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._91 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._65 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._53 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._3f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._5e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._6c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._97 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._0f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._90 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._d3 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._a7 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._b6 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._d5 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._a6 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._b9 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._a1 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._c3 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._c4 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._cd |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._cc |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._c2 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._e7 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._ce |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._e0 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._79 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._48 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._24 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._23 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._8d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._12 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._1d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._76 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._2b |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._8b |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._14 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/._25 |  | Source/configuration
01-rollback-netcode-server/.git/info/exclude |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/info/._exclude |  | Source/configuration
01-rollback-netcode-server/.git/logs/HEAD |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/logs/._HEAD |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/logs/._refs |  | Source/configuration
01-rollback-netcode-server/.git/hooks/commit-msg.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._commit-msg.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/pre-rebase.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._pre-rebase.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/sendemail-validate.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._sendemail-validate.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/pre-commit.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._pre-commit.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/applypatch-msg.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._applypatch-msg.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/fsmonitor-watchman.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._fsmonitor-watchman.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/pre-receive.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._pre-receive.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/prepare-commit-msg.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._prepare-commit-msg.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/post-update.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._post-update.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/pre-merge-commit.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._pre-merge-commit.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/pre-applypatch.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._pre-applypatch.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/pre-push.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._pre-push.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/update.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._update.sample | .sample | Source/configuration
01-rollback-netcode-server/.git/hooks/push-to-checkout.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/hooks/._push-to-checkout.sample | .sample | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/refs/._heads |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/refs/._tags |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/refs/._remotes |  | Source/configuration
01-rollback-netcode-server/frontend/app/ai-insights/page.tsx | .tsx | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/ai-insights/._page.tsx | .tsx | Source/configuration
01-rollback-netcode-server/frontend/app/dashboard/page.tsx | .tsx | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/dashboard/._page.tsx | .tsx | Source/configuration
01-rollback-netcode-server/frontend/app/components/Navbar.tsx | .tsx | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/components/._Navbar.tsx | .tsx | Source/configuration
01-rollback-netcode-server/frontend/app/arena/page.tsx | .tsx | Source/configuration
__MACOSX/01-rollback-netcode-server/frontend/app/arena/._page.tsx | .tsx | Source/configuration
01-rollback-netcode-server/backend/src/desync/detector.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/desync/._detector.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/desync/mod.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/desync/._mod.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/network/udp_server.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/network/._udp_server.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/network/mod.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/network/._mod.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/network/clock_sync.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/network/._clock_sync.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/simulation/rollback.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/simulation/._rollback.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/simulation/ring_buffer.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/simulation/._ring_buffer.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/simulation/mod.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/simulation/._mod.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/simulation/state.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/simulation/._state.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/protocol/mod.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/protocol/._mod.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/protocol/packets.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/protocol/._packets.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/math/fixed_point.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/math/._fixed_point.rs | .rs | Rust source
01-rollback-netcode-server/backend/src/math/mod.rs | .rs | Rust source
__MACOSX/01-rollback-netcode-server/backend/src/math/._mod.rs | .rs | Rust source
01-rollback-netcode-server/.git/objects/59/5d11734f621e683f256707e8dccf953e78159e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/59/._5d11734f621e683f256707e8dccf953e78159e |  | Source/configuration
01-rollback-netcode-server/.git/objects/59/03d8f5240f5c069b0a47331d624c227c93808a |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/59/._03d8f5240f5c069b0a47331d624c227c93808a |  | Source/configuration
01-rollback-netcode-server/.git/objects/0c/42a261012f53fb1b63c9ebb12da27afbce930e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/0c/._42a261012f53fb1b63c9ebb12da27afbce930e |  | Source/configuration
01-rollback-netcode-server/.git/objects/0c/e39531dafebaf986e7d6a174e4b7035b57061f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/0c/._e39531dafebaf986e7d6a174e4b7035b57061f |  | Source/configuration
01-rollback-netcode-server/.git/objects/68/41637be6bf393a37fa9eeefe11794db73feb54 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/68/._41637be6bf393a37fa9eeefe11794db73feb54 |  | Source/configuration
01-rollback-netcode-server/.git/objects/57/74ee7bde43273dab5f3dc57924edf7148033ea |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/57/._74ee7bde43273dab5f3dc57924edf7148033ea |  | Source/configuration
01-rollback-netcode-server/.git/objects/57/25744945dc8ccbba0faeb9d535dca49c2ecbc1 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/57/._25744945dc8ccbba0faeb9d535dca49c2ecbc1 |  | Source/configuration
01-rollback-netcode-server/.git/objects/57/2615ade3349a5ae52a42cf726936fddcf2ce6b |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/57/._2615ade3349a5ae52a42cf726936fddcf2ce6b |  | Source/configuration
01-rollback-netcode-server/.git/objects/03/9dadbaf8783cbdf8ac4aef56bcc862e493e9e0 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/03/._9dadbaf8783cbdf8ac4aef56bcc862e493e9e0 |  | Source/configuration
01-rollback-netcode-server/.git/objects/03/9624775b001e5a9022ae751fad4b87dd80b959 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/03/._9624775b001e5a9022ae751fad4b87dd80b959 |  | Source/configuration
01-rollback-netcode-server/.git/objects/03/421bd8311b309da2990521fceb3c4d6d8e514d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/03/._421bd8311b309da2990521fceb3c4d6d8e514d |  | Source/configuration
01-rollback-netcode-server/.git/objects/04/2b913e3216a1ded5537b4d4ae00751d0867c97 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/04/._2b913e3216a1ded5537b4d4ae00751d0867c97 |  | Source/configuration
01-rollback-netcode-server/.git/objects/69/129e26d8899d4f69809344ee2ec783b9763aca |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/69/._129e26d8899d4f69809344ee2ec783b9763aca |  | Source/configuration
01-rollback-netcode-server/.git/objects/3c/1debaebc41fd7278abc42b61096681ec43315c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/3c/._1debaebc41fd7278abc42b61096681ec43315c |  | Source/configuration
01-rollback-netcode-server/.git/objects/51/0b6fc585e589db563b3aa74b0d66c282a522fa |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/51/._0b6fc585e589db563b3aa74b0d66c282a522fa |  | Source/configuration
01-rollback-netcode-server/.git/objects/58/7c420026777831742e53b423683404f02a1b29 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/58/._7c420026777831742e53b423683404f02a1b29 |  | Source/configuration
01-rollback-netcode-server/.git/objects/0b/40c549087e4cb115cdda0a31fbcf2f0ea741ab |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/0b/._40c549087e4cb115cdda0a31fbcf2f0ea741ab |  | Source/configuration
01-rollback-netcode-server/.git/objects/0b/46ae30f6fe14d2f02788ba436f760d7eb77da8 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/0b/._46ae30f6fe14d2f02788ba436f760d7eb77da8 |  | Source/configuration
01-rollback-netcode-server/.git/objects/5a/f1426d8ffd3ac118076790ef98cf5b576e9d75 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/5a/._f1426d8ffd3ac118076790ef98cf5b576e9d75 |  | Source/configuration
01-rollback-netcode-server/.git/objects/5f/23224588ef2a22748eb4de8516fc90b3a96047 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/5f/._23224588ef2a22748eb4de8516fc90b3a96047 |  | Source/configuration
01-rollback-netcode-server/.git/objects/33/ad091d26d8a9dc95ebdf616e217d985ec215b8 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/33/._ad091d26d8a9dc95ebdf616e217d985ec215b8 |  | Source/configuration
01-rollback-netcode-server/.git/objects/33/d16f01a2e32fbe5b7776cc6413bf464792996b |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/33/._d16f01a2e32fbe5b7776cc6413bf464792996b |  | Source/configuration
01-rollback-netcode-server/.git/objects/a4/99c225bfed08f49cda8744e81331931b1d5149 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/a4/._99c225bfed08f49cda8744e81331931b1d5149 |  | Source/configuration
01-rollback-netcode-server/.git/objects/ad/b3dc13cf3acbc2fcedb40730feed645c17810c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/ad/._b3dc13cf3acbc2fcedb40730feed645c17810c |  | Source/configuration
01-rollback-netcode-server/.git/objects/d7/f1d5c9a1cde0aadb57954fb8b6460d9d3dedbe |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/d7/._f1d5c9a1cde0aadb57954fb8b6460d9d3dedbe |  | Source/configuration
01-rollback-netcode-server/.git/objects/d7/9a064146dc5cff2cf90c2588b7b8773cdb0938 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/d7/._9a064146dc5cff2cf90c2588b7b8773cdb0938 |  | Source/configuration
01-rollback-netcode-server/.git/objects/be/d4e947fce93db7417f19d005cde39fc530e84e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/be/._d4e947fce93db7417f19d005cde39fc530e84e |  | Source/configuration
01-rollback-netcode-server/.git/objects/df/06b45272fae80cbba7be382ecb63d54df0975e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/df/._06b45272fae80cbba7be382ecb63d54df0975e |  | Source/configuration
01-rollback-netcode-server/.git/objects/d6/4be6949b49dbd34541f58425f504a0ab31a489 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/d6/._4be6949b49dbd34541f58425f504a0ab31a489 |  | Source/configuration
01-rollback-netcode-server/.git/objects/bc/bf8614cea4c709f2f937152e939582440564f6 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/bc/._bf8614cea4c709f2f937152e939582440564f6 |  | Source/configuration
01-rollback-netcode-server/.git/objects/f4/5d1193e0a3982c307a9ceacd406037b8de0385 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/f4/._5d1193e0a3982c307a9ceacd406037b8de0385 |  | Source/configuration
01-rollback-netcode-server/.git/objects/f3/d8cbc06678a09afc948e1f4c852ee0f8f913a5 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/f3/._d8cbc06678a09afc948e1f4c852ee0f8f913a5 |  | Source/configuration
01-rollback-netcode-server/.git/objects/ee/c03731adc6b1042527810984b2707e88798eee |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/ee/._c03731adc6b1042527810984b2707e88798eee |  | Source/configuration
01-rollback-netcode-server/.git/objects/fc/43b7471c74a1e3305ad5fab3de5b52bcc7fa8c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/fc/._43b7471c74a1e3305ad5fab3de5b52bcc7fa8c |  | Source/configuration
01-rollback-netcode-server/.git/objects/f5/80dd36c6ca903e25305a0874c47db74c05bf83 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/f5/._80dd36c6ca903e25305a0874c47db74c05bf83 |  | Source/configuration
01-rollback-netcode-server/.git/objects/e3/2fa5cb7c5e2c776b473274fe6821874d778fee |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/e3/._2fa5cb7c5e2c776b473274fe6821874d778fee |  | Source/configuration
01-rollback-netcode-server/.git/objects/cf/875f87d5355e19ca2eb440c145f18448d4d99a |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/cf/._875f87d5355e19ca2eb440c145f18448d4d99a |  | Source/configuration
01-rollback-netcode-server/.git/objects/e4/5f7f729e5747cd0f83be947dc0424a770a5307 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/e4/._5f7f729e5747cd0f83be947dc0424a770a5307 |  | Source/configuration
01-rollback-netcode-server/.git/objects/c1/b14a966845d2a855f9d94a59c0daa1d1ddcde0 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/c1/._b14a966845d2a855f9d94a59c0daa1d1ddcde0 |  | Source/configuration
01-rollback-netcode-server/.git/objects/4e/5f5d8987dd25c3995b88d23d3042e39be9b176 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/4e/._5f5d8987dd25c3995b88d23d3042e39be9b176 |  | Source/configuration
01-rollback-netcode-server/.git/objects/29/ab179f9061cbde7b593221ab72f37e0ad9fdb0 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/29/._ab179f9061cbde7b593221ab72f37e0ad9fdb0 |  | Source/configuration
01-rollback-netcode-server/.git/objects/45/8bfefc7d0ef1e546b2112276346b23259e60d2 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/45/._8bfefc7d0ef1e546b2112276346b23259e60d2 |  | Source/configuration
01-rollback-netcode-server/.git/objects/45/2b851ac2036819b29fb802f71a2469635bc9b4 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/45/._2b851ac2036819b29fb802f71a2469635bc9b4 |  | Source/configuration
01-rollback-netcode-server/.git/objects/1f/541d70a675f85ad517ac698c8457f87ba5ea0e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/1f/._541d70a675f85ad517ac698c8457f87ba5ea0e |  | Source/configuration
01-rollback-netcode-server/.git/objects/1f/bb4b3b11194aae9aff0627692e755d97a0a7ea |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/1f/._bb4b3b11194aae9aff0627692e755d97a0a7ea |  | Source/configuration
01-rollback-netcode-server/.git/objects/87/2e5200b579e02d88ec262872c36d299a2a2ce3 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/87/._2e5200b579e02d88ec262872c36d299a2a2ce3 |  | Source/configuration
01-rollback-netcode-server/.git/objects/7b/ac586cd37d11b92e24ab73a07933090c8136cb |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/7b/._ac586cd37d11b92e24ab73a07933090c8136cb |  | Source/configuration
01-rollback-netcode-server/.git/objects/8f/9ee7d5cea83b735c97f162cd1edbc4561cf184 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/8f/._9ee7d5cea83b735c97f162cd1edbc4561cf184 |  | Source/configuration
01-rollback-netcode-server/.git/objects/10/ab2637fdcdaae965c35d5451f0c6ef4efd3313 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/10/._ab2637fdcdaae965c35d5451f0c6ef4efd3313 |  | Source/configuration
01-rollback-netcode-server/.git/objects/43/35184d051902aeb291c7335d21d4dca9c0d5cf |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/43/._35184d051902aeb291c7335d21d4dca9c0d5cf |  | Source/configuration
01-rollback-netcode-server/.git/objects/43/16c804ca8984daf4c0ac6c52673e3636e16846 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/43/._16c804ca8984daf4c0ac6c52673e3636e16846 |  | Source/configuration
01-rollback-netcode-server/.git/objects/9f/1390dd9a37348ac51b99d3874d4677c9053c8c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/9f/._1390dd9a37348ac51b99d3874d4677c9053c8c |  | Source/configuration
01-rollback-netcode-server/.git/objects/07/d212b67f3f29cd8f2b3ab02f973a9f65707d20 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/07/._d212b67f3f29cd8f2b3ab02f973a9f65707d20 |  | Source/configuration
01-rollback-netcode-server/.git/objects/5c/ef6d28db06fa278dbd6e01e2b151b5e127603d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/5c/._ef6d28db06fa278dbd6e01e2b151b5e127603d |  | Source/configuration
01-rollback-netcode-server/.git/objects/5c/0e6026fbe4ff08f0675422e803267dd25e173d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/5c/._0e6026fbe4ff08f0675422e803267dd25e173d |  | Source/configuration
01-rollback-netcode-server/.git/objects/09/f2c89ca8eee022a036ca4d0aab65167149e850 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/09/._f2c89ca8eee022a036ca4d0aab65167149e850 |  | Source/configuration
01-rollback-netcode-server/.git/objects/5d/bf851e84cf7980d80835b732b32f6180bc244d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/5d/._bf851e84cf7980d80835b732b32f6180bc244d |  | Source/configuration
01-rollback-netcode-server/.git/objects/91/0a93af6cc6d75c9108d482d198c73b283cae73 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/91/._0a93af6cc6d75c9108d482d198c73b283cae73 |  | Source/configuration
01-rollback-netcode-server/.git/objects/65/c3fa3031a0fad7bea4af11f5ed98d4702025e9 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/65/._c3fa3031a0fad7bea4af11f5ed98d4702025e9 |  | Source/configuration
01-rollback-netcode-server/.git/objects/53/4a957317f47dbbfed31cd7059732aaf55216e1 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/53/._4a957317f47dbbfed31cd7059732aaf55216e1 |  | Source/configuration
01-rollback-netcode-server/.git/objects/3f/e12a2d923fda3b1a625e2f929ffefa29454587 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/3f/._e12a2d923fda3b1a625e2f929ffefa29454587 |  | Source/configuration
01-rollback-netcode-server/.git/objects/5e/fdb4d5fe9a3fd63b088c9fae98e398ad348fbd |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/5e/._fdb4d5fe9a3fd63b088c9fae98e398ad348fbd |  | Source/configuration
01-rollback-netcode-server/.git/objects/6c/2977353a85254eb2c0e8f3544f964628cc4882 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/6c/._2977353a85254eb2c0e8f3544f964628cc4882 |  | Source/configuration
01-rollback-netcode-server/.git/objects/97/5f3300f8db61f0ebd43a361ba7d39229b3f715 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/97/._5f3300f8db61f0ebd43a361ba7d39229b3f715 |  | Source/configuration
01-rollback-netcode-server/.git/objects/0f/a87ca58213e53d924852a845597a83d87c67a4 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/0f/._a87ca58213e53d924852a845597a83d87c67a4 |  | Source/configuration
01-rollback-netcode-server/.git/objects/90/0f5af8f5d07b4e59997c17a9bad45bf3076539 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/90/._0f5af8f5d07b4e59997c17a9bad45bf3076539 |  | Source/configuration
01-rollback-netcode-server/.git/objects/d3/2171f53c9a1fa89e447c7fc09b15591407437c |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/d3/._2171f53c9a1fa89e447c7fc09b15591407437c |  | Source/configuration
01-rollback-netcode-server/.git/objects/d3/ef40494e00215a8d91893c87ca0c9140fb5d18 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/d3/._ef40494e00215a8d91893c87ca0c9140fb5d18 |  | Source/configuration
01-rollback-netcode-server/.git/objects/a7/1e9d423e4e2edec92883f3a89606c3cceb8703 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/a7/._1e9d423e4e2edec92883f3a89606c3cceb8703 |  | Source/configuration
01-rollback-netcode-server/.git/objects/b6/947fbfa3ca1fe9e1bdfd8ca2e17272f66309eb |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/b6/._947fbfa3ca1fe9e1bdfd8ca2e17272f66309eb |  | Source/configuration
01-rollback-netcode-server/.git/objects/d5/e993ed947ca8ed20b887e990453ca71b084277 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/d5/._e993ed947ca8ed20b887e990453ca71b084277 |  | Source/configuration
01-rollback-netcode-server/.git/objects/a6/8371ced4b26e9c8f5525d0d1e4601ce4c1d042 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/a6/._8371ced4b26e9c8f5525d0d1e4601ce4c1d042 |  | Source/configuration
01-rollback-netcode-server/.git/objects/b9/25a426e0fdcd58b1af550152ab045996a909e3 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/b9/._25a426e0fdcd58b1af550152ab045996a909e3 |  | Source/configuration
01-rollback-netcode-server/.git/objects/a1/ca95c9f16c7872da5063bb42137b2df306d505 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/a1/._ca95c9f16c7872da5063bb42137b2df306d505 |  | Source/configuration
01-rollback-netcode-server/.git/objects/c3/d776d731b41b31a6e60e00213f7eeb6c99489d |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/c3/._d776d731b41b31a6e60e00213f7eeb6c99489d |  | Source/configuration
01-rollback-netcode-server/.git/objects/c3/4d2c154d879ae96e16fe0b53165cef298f180f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/c3/._4d2c154d879ae96e16fe0b53165cef298f180f |  | Source/configuration
01-rollback-netcode-server/.git/objects/c4/a6337dc1f059caf12c0973119959184770cdfa |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/c4/._a6337dc1f059caf12c0973119959184770cdfa |  | Source/configuration
01-rollback-netcode-server/.git/objects/cd/685551e8d83e3ee39d80e42044b6637d5b0ac4 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/cd/._685551e8d83e3ee39d80e42044b6637d5b0ac4 |  | Source/configuration
01-rollback-netcode-server/.git/objects/cc/dd47b07410a98771dc822f7fc72d32994467cb |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/cc/._dd47b07410a98771dc822f7fc72d32994467cb |  | Source/configuration
01-rollback-netcode-server/.git/objects/c2/3760953e223a7a326e84be6d448d452ccfd908 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/c2/._3760953e223a7a326e84be6d448d452ccfd908 |  | Source/configuration
01-rollback-netcode-server/.git/objects/e7/ff90fd2767199e09b281bfa87e08a90f33270e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/e7/._ff90fd2767199e09b281bfa87e08a90f33270e |  | Source/configuration
01-rollback-netcode-server/.git/objects/e7/6bf2d4bad45b7cec365a63ad3738ed70d861de |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/e7/._6bf2d4bad45b7cec365a63ad3738ed70d861de |  | Source/configuration
01-rollback-netcode-server/.git/objects/ce/8d7ad36688e6861df77e9e242f9cfc956d2dd2 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/ce/._8d7ad36688e6861df77e9e242f9cfc956d2dd2 |  | Source/configuration
01-rollback-netcode-server/.git/objects/ce/578db33bf83a8c1fba0ad7ebff4f971c940fb5 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/ce/._578db33bf83a8c1fba0ad7ebff4f971c940fb5 |  | Source/configuration
01-rollback-netcode-server/.git/objects/e0/177d61c4e6c96f2ec7d0185186dc05a74172ed |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/e0/._177d61c4e6c96f2ec7d0185186dc05a74172ed |  | Source/configuration
01-rollback-netcode-server/.git/objects/79/b230d8a4a539206765655e1302e637984ec193 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/79/._b230d8a4a539206765655e1302e637984ec193 |  | Source/configuration
01-rollback-netcode-server/.git/objects/79/11da969af038bcb1a4c65b45156f4dab3b14cb |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/79/._11da969af038bcb1a4c65b45156f4dab3b14cb |  | Source/configuration
01-rollback-netcode-server/.git/objects/48/d2d0ab65483297631f81794bf0b39f1d77b6fb |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/48/._d2d0ab65483297631f81794bf0b39f1d77b6fb |  | Source/configuration
01-rollback-netcode-server/.git/objects/24/8c251f4c156cce8e9bc493b35385bef20d7095 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/24/._8c251f4c156cce8e9bc493b35385bef20d7095 |  | Source/configuration
01-rollback-netcode-server/.git/objects/24/3db5c0bcef6cb34d0d348793d1e0424d8e3970 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/24/._3db5c0bcef6cb34d0d348793d1e0424d8e3970 |  | Source/configuration
01-rollback-netcode-server/.git/objects/23/8c37d34c1cacc9751c674990986c6424615246 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/23/._8c37d34c1cacc9751c674990986c6424615246 |  | Source/configuration
01-rollback-netcode-server/.git/objects/8d/ec6ed2909cbae29af8054f9e239ceb7f0f50ec |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/8d/._ec6ed2909cbae29af8054f9e239ceb7f0f50ec |  | Source/configuration
01-rollback-netcode-server/.git/objects/8d/940eb0cf785551910d93682ed305ab10429434 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/8d/._940eb0cf785551910d93682ed305ab10429434 |  | Source/configuration
01-rollback-netcode-server/.git/objects/12/d9e515e65ef9ffca26181d2e68876d36d97223 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/12/._d9e515e65ef9ffca26181d2e68876d36d97223 |  | Source/configuration
01-rollback-netcode-server/.git/objects/1d/0e8a07ea5ce5d6c346da82803e5e6ac3ff0f8e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/1d/._0e8a07ea5ce5d6c346da82803e5e6ac3ff0f8e |  | Source/configuration
01-rollback-netcode-server/.git/objects/1d/29190f1a52b3ea2ec6a972caaffc4581079d0e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/1d/._29190f1a52b3ea2ec6a972caaffc4581079d0e |  | Source/configuration
01-rollback-netcode-server/.git/objects/76/347aec39a9612728f26391cd8b4c90f718740e |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/76/._347aec39a9612728f26391cd8b4c90f718740e |  | Source/configuration
01-rollback-netcode-server/.git/objects/2b/6c365be6da529909eea4a858ec4deb298b1c2f |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/2b/._6c365be6da529909eea4a858ec4deb298b1c2f |  | Source/configuration
01-rollback-netcode-server/.git/objects/2b/328eb05ad25689b2fddc16d7d52db933abef97 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/2b/._328eb05ad25689b2fddc16d7d52db933abef97 |  | Source/configuration
01-rollback-netcode-server/.git/objects/8b/72d18c37d36a260ed1b05f283e3a3d7e299e19 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/8b/._72d18c37d36a260ed1b05f283e3a3d7e299e19 |  | Source/configuration
01-rollback-netcode-server/.git/objects/14/254afe753781babe2636371c496fb6700a7cd0 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/14/._254afe753781babe2636371c496fb6700a7cd0 |  | Source/configuration
01-rollback-netcode-server/.git/objects/25/9a50788fa0b4722782e5e8378cf85f612d865b |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/25/._9a50788fa0b4722782e5e8378cf85f612d865b |  | Source/configuration
01-rollback-netcode-server/.git/objects/25/23102b1016640a5dc032a5951f98d275409210 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/objects/25/._23102b1016640a5dc032a5951f98d275409210 |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/logs/refs/._heads |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/logs/refs/._remotes |  | Source/configuration
01-rollback-netcode-server/.git/refs/heads/main |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/refs/heads/._main |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/refs/remotes/._origin |  | Source/configuration
01-rollback-netcode-server/.git/logs/refs/heads/main |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/logs/refs/heads/._main |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/logs/refs/remotes/._origin |  | Source/configuration
01-rollback-netcode-server/.git/refs/remotes/origin/main |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/refs/remotes/origin/._main |  | Source/configuration
01-rollback-netcode-server/.git/logs/refs/remotes/origin/main |  | Source/configuration
__MACOSX/01-rollback-netcode-server/.git/logs/refs/remotes/origin/._main |  | Source/configuration